## Batch6-Group1
WellsFargo Java Training Sprint Template
PROJECT NAME: LOAN MANAGMENT SYSTEM - JAVA WITH REACT CASE STUDY |  |  |  | Trainer |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
Batch #: | 6 | Group #: 1 , | Particiaonts name:Shaurya Shankar Rushil Goel Priyansh Jain Vedant Mukund Barsagade |  |  |  | 2023-09-06 | 2023-08-29 | 3.03% | SCOPE STATEMENT
At Risk? | SPRINT # | USER STORY | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Yes | SPRINT - 01 Setup & User Authentication | US-01 - As a developer, develop a well-organized project layout and be able to create an initial React application that includes the ability to navigate between different pages. | 1. Set up a new React project using Create React App |  | Shaurya |  | 2023-09-06 | 2023-09-06 | 1 | Complete | High
No |  |  | 2. Install and configure React Router for handling routing in the application |  | Shaurya, Priyansh |  | 2023-09-06 | 2023-09-06 |  | In Progress | Medium
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | Vedant, Rushil |  | 2023-09-06 | 2023-09-06 |  | Complete | Low
|  | US_02 - As a database developer, you need to easily establish the necessary database structure and create the required databases and tables to efficiently store and manage my data. | 1. Design the database schema for the online banking system |  | User 1 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 2. Create the table for registered users |  | User 2 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 3. Create the table for the account |  | User 3 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 4. Create the table for Transactions |  | User 4 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 5. Populate all the above tables with sample data space |  | User 5 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  | US_03 - As a frontend developer, create a user registration form that allows end user to fill out details and register as a new user, and have that information securely processed by the backend system. | 1. Create a react page to read user details and provide proper validations at backend |  | User 1 |  | 2023-09-07 | 2023-09-07 | 1 | Not Started
|  |  | 2. Write a proper api end point in springboot to read data from frontend and insert into database |  | User 2 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  |  | 3. Perform all sorts of validations using springboot's validators |  | User 3 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  | US_04 - As a frontend user, develop a secure way to access the application through a login page for an end user to authenticate and ensure only authorized individuals can access the system. | 1. create a react login page to read username and password |  | User 1 |  | 2023-08-10 | 2023-08-10 | 1 | Not Started
|  |  | 2. Include the Authentication and Authorization techniques |  | User 2 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 3.Write a proper api's to read data from front end and implement authentication and authorization using spring security |  | User 3 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 4. Implement authentication using JWT |  | User 4 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 5. Perform the session management |  | User 5 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  | US_05 - As a developer, create a user-friendly form that allows end user to create a new account as a registered user and the information provided by the end user to be securely processed by the backend system and accurately stored in the database. | 1. Create a react form to create a new account for registered users |  | User 1 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 2. upon successful adding the data, it should generate a unique id, which should also sent along with other details for backend processing. |  | User 2 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 3. Write the backend springboot api's to read account details and add it to database |  | User 3 |  | 2028-08-10 | 2028-08-10 |  | Not Started
| SPRINT - 02 Account Management & User Dashboard | US_07 - As a developer, create a visually appealing dashboard for the end user that provides easy access to a range of operations and tasks they can perform. This dashboard should enable end user to conveniently navigate through different features and carry out various actions. | 1. Design the user interface for the user dashboard. |  | User 1 |  | 2028-08-11 | 2028-08-11 | 1 | Not Started
|  |  | 2. Implement the user dashboard page in React. |  | User 2 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 3. Connect the user dashboard to the backend API to fetch relevant data. write the springboot implementation to fetch all user data for respective user and send to UI |  | User 3 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 4. Implement functionality in the user dashboard, such as View Loans, Items Purchased, Apply for Loan |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 5. Test the user dashboard's functionality and user experience. |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  | US_08 - As a developer, create the a dashboard to end user to view loan cards & Apply Loan. Create a backend layer to support view loan and loan processing. | 1. Create a page for user to purchase a product from the available list, by providing the appropriate details, with acceptance criteria as mentioned |  | User 1 |  | 2028-08-14 | 2028-08-14 | 1 | Not Started
|  |  | 2. An user should be able to view all the loan cards availed with criteria It should display only the active loan cards. |  | User 2 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object. Read the loan details from UI and pass it to service layer further to do layer based on item selected, it should identify the appropriate card type and amount, do the processing . Must use POST method of communication |  | User 3 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 4. Based on the employee id logged in, it should find and display the appropriate active loans Must use POST method of communication |  | User 4 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  | US_09 - As a developer, create a front end page to perform purchase and show the purchase history. | 1. Create a react page to view all the items purchased. It should display all the products which are purchased, both active loans and completed loans. |  | User 1 |  | 2028-08-16 | 2028-08-16 | 1 | Not Started
|  |  | 2. Should be able to extract the values from request body object |  | User 2 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 3. Based on the employee id logged in, it should find all the items purchased by the employee and returns them in the form of grid. |  | User 3 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | Must use POST method of communication |  | User 4 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 5. write the backend processing to read the data from database and send it to frontend. It must have a provision to redirect to home or dashboard upon successful display. |  | User 5 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  | US_10 - As a developer, test and ensure that all the front end and backend units are working fine and integrated successfully. Make sure that the end user to have a smooth and error-free experience when using the application. | 1. Write unit tests to ensure the functionality of critical components |  | User 1 |  | 2028-08-17 | 2028-08-17 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 2 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 3 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  | US_11 - As a frontend developer, create a admin page that allows admin to provide the user id and password for validation. | 1. DB Schema creation and setup in mysql database 2. Spring boot project setup creation. 3. Develop the post method api to read data from view page. 4. Use appropriate DTO objects for view and data integration 5. Use spring data jpa for connecting to databases. |  | User 1 &2 |  | 2028-08-18 | 2028-08-18 | 1 | Not Started
|  |  | 6. Set up the appropriate methods to perform functions like user validation, user registration, transaction management, transaction details. |  | User 3 &4 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 7. Both username and password are mandatory, if not provided, error messages should be displayed. |  | User 5 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 8. Successful validation should redirect to menu page, unsuccessful validation should redirect to registration page. |  |  |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  | US_12 - As a developer, create a front end admin login page, display the Admin Dashboard for Loan, Customer and Item Master details management. Create a backend layer to support view Loan Card Details Management processing | 1. Should be able to extract the values from request body object |  |  |  | 2028-08-21 | 2028-08-21 | 1 | Not Started
|  |  | 2. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database. |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 3. Should return the model object after successful insertion of data |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 4. Must use POST method of communication |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  | US_13 - As a developer, create a front end admin page to 1. To create a new loan card with the following details viz., loand_id, loan_type, duration_in_years and should save it in the database. 2. To create a new employee with the following details: viz., employee_id, employee_name, designation, department, gender, date_of_birth, date_of_joining. | 1. Once the loan card data is entered, it should redirect to display all the existing loan card details and also have a provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 | 1 | Not Started
|  |  | 2. Once the employee data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 4. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 5. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 6. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  | US_14 - As a developer, create a front end admin page with item management, to create a new item details Create a backend layer to support on item master management | 1. As an admin he should be able to create a new item details with the following details: viz., item_id, item_description, issue_status, item_make, item_category, item_valuation. |  |  |  | 2028-08-23 | 2028-08-23 | 1 | Not Started
|  |  | 2.Once the data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object, 4. Should return the model object after successful insertion of data 5. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 6. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 7. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
Yes | SPRINT - 03 Error handling & Design Enhancement | US_11 - As a developer, implement a proper error handling mechanism, so that the end user, to receives a clear and understandable error messages to know what went wrong. | 1. Create a custom exception objects in backend to raise when user details not found, insufficient balance, no transactions etc., |  | User 1 |  | 2028-08-24 | 2028-08-24 | 1 | Not Started | High
No |  |  | Implement the custom exception logic at UI level |  | User 2 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Medium
|  |  | 2. All input validations logic must be performed at UI level |  | User 3 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Low
|  |  | 3. All data validations must be performed at backend |  | User 1 |  | 2028-08-24 | 2028-08-24 |  | Not Started
|  | US_12 - As a developer, rigourously test the app and ensure all the front end and backend units are working fine and integrated successfully | 1. Write unit tests to ensure the functionality of critical components |  | User 2 |  | 2028-08-25 | 2028-08-25 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 3 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 4 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  | US_13 - UI Design Enhancements - Make sure there is an improvements in the overall design and user interface of the application to enhance the user experience and make it more visually appealing. | 1. Design the Front-End UI of the application with proper Home Page |  | User 1 |  | 2028-08-28 | 2028-08-28 | 1 | Not Started
|  |  | 2. Improve the user interface by adding responsive design, styling, and enhancing the user experience |  | User 2 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  |  | 3. Ensure accessibility and compatibility across different browsers |  | User 3 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  | Final Project Presentation |  |  |  |  | 2028-08-29 | 2028-08-29 | 1 | Not Started

## Batch6-Group2
WellsFargo Java Training Sprint Template
PROJECT NAME: LOAN MANAGMENT SYSTEM - JAVA WITH REACT CASE STUDY |  |  |  | Trainer |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
Batch #: |  | Group #: 1 , | Particiaonts name: Viswonathan Manoranjan Akash Kumar Harsh M Gunda Sai Sathvik |  |  |  | 2023-09-06 | 2023-08-29 | 3.03% | SCOPE STATEMENT
At Risk? | SPRINT # | USER STORY | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Yes | SPRINT - 01 Setup & User Authentication | US-01 - As a developer, develop a well-organized project layout and be able to create an initial React application that includes the ability to navigate between different pages. | 1. Set up a new React project using Create React App |  | Akash, Satvik |  | 2023-09-06 | 2023-09-06 | 1 | Complete | High
No |  |  | 2. Install and configure React Router for handling routing in the application |  | Akash, Satvik |  | 2023-09-06 | 2023-09-06 |  | In Progress | Medium
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | Harsh,Vishnathan |  | 2023-09-06 | 2023-09-06 |  | Complete | Low
|  | US_02 - As a database developer, you need to easily establish the necessary database structure and create the required databases and tables to efficiently store and manage my data. | 1. Design the database schema for the online banking system |  | User 1 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 2. Create the table for registered users |  | User 2 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 3. Create the table for the account |  | User 3 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 4. Create the table for Transactions |  | User 4 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 5. Populate all the above tables with sample data space |  | User 5 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  | US_03 - As a frontend developer, create a user registration form that allows end user to fill out details and register as a new user, and have that information securely processed by the backend system. | 1. Create a react page to read user details and provide proper validations at backend |  | User 1 |  | 2023-09-07 | 2023-09-07 | 1 | Not Started
|  |  | 2. Write a proper api end point in springboot to read data from frontend and insert into database |  | User 2 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  |  | 3. Perform all sorts of validations using springboot's validators |  | User 3 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  | US_04 - As a frontend user, develop a secure way to access the application through a login page for an end user to authenticate and ensure only authorized individuals can access the system. | 1. create a react login page to read username and password |  | User 1 |  | 2023-08-10 | 2023-08-10 | 1 | Not Started
|  |  | 2. Include the Authentication and Authorization techniques |  | User 2 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 3.Write a proper api's to read data from front end and implement authentication and authorization using spring security |  | User 3 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 4. Implement authentication using JWT |  | User 4 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 5. Perform the session management |  | User 5 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  | US_05 - As a developer, create a user-friendly form that allows end user to create a new account as a registered user and the information provided by the end user to be securely processed by the backend system and accurately stored in the database. | 1. Create a react form to create a new account for registered users |  | User 1 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 2. upon successful adding the data, it should generate a unique id, which should also sent along with other details for backend processing. |  | User 2 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 3. Write the backend springboot api's to read account details and add it to database |  | User 3 |  | 2028-08-10 | 2028-08-10 |  | Not Started
| SPRINT - 02 Account Management & User Dashboard | US_07 - As a developer, create a visually appealing dashboard for the end user that provides easy access to a range of operations and tasks they can perform. This dashboard should enable end user to conveniently navigate through different features and carry out various actions. | 1. Design the user interface for the user dashboard. |  | User 1 |  | 2028-08-11 | 2028-08-11 | 1 | Not Started
|  |  | 2. Implement the user dashboard page in React. |  | User 2 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 3. Connect the user dashboard to the backend API to fetch relevant data. write the springboot implementation to fetch all user data for respective user and send to UI |  | User 3 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 4. Implement functionality in the user dashboard, such as View Loans, Items Purchased, Apply for Loan |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 5. Test the user dashboard's functionality and user experience. |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  | US_08 - As a developer, create the a dashboard to end user to view loan cards & Apply Loan. Create a backend layer to support view loan and loan processing. | 1. Create a page for user to purchase a product from the available list, by providing the appropriate details, with acceptance criteria as mentioned |  | User 1 |  | 2028-08-14 | 2028-08-14 | 1 | Not Started
|  |  | 2. An user should be able to view all the loan cards availed with criteria It should display only the active loan cards. |  | User 2 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object. Read the loan details from UI and pass it to service layer further to do layer based on item selected, it should identify the appropriate card type and amount, do the processing . Must use POST method of communication |  | User 3 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 4. Based on the employee id logged in, it should find and display the appropriate active loans Must use POST method of communication |  | User 4 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  | US_09 - As a developer, create a front end page to perform purchase and show the purchase history. | 1. Create a react page to view all the items purchased. It should display all the products which are purchased, both active loans and completed loans. |  | User 1 |  | 2028-08-16 | 2028-08-16 | 1 | Not Started
|  |  | 2. Should be able to extract the values from request body object |  | User 2 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 3. Based on the employee id logged in, it should find all the items purchased by the employee and returns them in the form of grid. |  | User 3 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | Must use POST method of communication |  | User 4 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 5. write the backend processing to read the data from database and send it to frontend. It must have a provision to redirect to home or dashboard upon successful display. |  | User 5 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  | US_10 - As a developer, test and ensure that all the front end and backend units are working fine and integrated successfully. Make sure that the end user to have a smooth and error-free experience when using the application. | 1. Write unit tests to ensure the functionality of critical components |  | User 1 |  | 2028-08-17 | 2028-08-17 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 2 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 3 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  | US_11 - As a frontend developer, create a admin page that allows admin to provide the user id and password for validation. | 1. DB Schema creation and setup in mysql database 2. Spring boot project setup creation. 3. Develop the post method api to read data from view page. 4. Use appropriate DTO objects for view and data integration 5. Use spring data jpa for connecting to databases. |  | User 1 &2 |  | 2028-08-18 | 2028-08-18 | 1 | Not Started
|  |  | 6. Set up the appropriate methods to perform functions like user validation, user registration, transaction management, transaction details. |  | User 3 &4 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 7. Both username and password are mandatory, if not provided, error messages should be displayed. |  | User 5 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 8. Successful validation should redirect to menu page, unsuccessful validation should redirect to registration page. |  |  |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  | US_12 - As a developer, create a front end admin login page, display the Admin Dashboard for Loan, Customer and Item Master details management. Create a backend layer to support view Loan Card Details Management processing | 1. Should be able to extract the values from request body object |  |  |  | 2028-08-21 | 2028-08-21 | 1 | Not Started
|  |  | 2. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database. |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 3. Should return the model object after successful insertion of data |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 4. Must use POST method of communication |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  | US_13 - As a developer, create a front end admin page to 1. To create a new loan card with the following details viz., loand_id, loan_type, duration_in_years and should save it in the database. 2. To create a new employee with the following details: viz., employee_id, employee_name, designation, department, gender, date_of_birth, date_of_joining. | 1. Once the loan card data is entered, it should redirect to display all the existing loan card details and also have a provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 | 1 | Not Started
|  |  | 2. Once the employee data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 4. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 5. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 6. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  | US_14 - As a developer, create a front end admin page with item management, to create a new item details Create a backend layer to support on item master management | 1. As an admin he should be able to create a new item details with the following details: viz., item_id, item_description, issue_status, item_make, item_category, item_valuation. |  |  |  | 2028-08-23 | 2028-08-23 | 1 | Not Started
|  |  | 2.Once the data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object, 4. Should return the model object after successful insertion of data 5. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 6. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 7. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
Yes | SPRINT - 03 Error handling & Design Enhancement | US_11 - As a developer, implement a proper error handling mechanism, so that the end user, to receives a clear and understandable error messages to know what went wrong. | 1. Create a custom exception objects in backend to raise when user details not found, insufficient balance, no transactions etc., |  | User 1 |  | 2028-08-24 | 2028-08-24 | 1 | Not Started | High
No |  |  | Implement the custom exception logic at UI level |  | User 2 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Medium
|  |  | 2. All input validations logic must be performed at UI level |  | User 3 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Low
|  |  | 3. All data validations must be performed at backend |  | User 1 |  | 2028-08-24 | 2028-08-24 |  | Not Started
|  | US_12 - As a developer, rigourously test the app and ensure all the front end and backend units are working fine and integrated successfully | 1. Write unit tests to ensure the functionality of critical components |  | User 2 |  | 2028-08-25 | 2028-08-25 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 3 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 4 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  | US_13 - UI Design Enhancements - Make sure there is an improvements in the overall design and user interface of the application to enhance the user experience and make it more visually appealing. | 1. Design the Front-End UI of the application with proper Home Page |  | User 1 |  | 2028-08-28 | 2028-08-28 | 1 | Not Started
|  |  | 2. Improve the user interface by adding responsive design, styling, and enhancing the user experience |  | User 2 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  |  | 3. Ensure accessibility and compatibility across different browsers |  | User 3 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  | Final Project Presentation |  |  |  |  | 2028-08-29 | 2028-08-29 | 1 | Not Started

## Batch6-Group3
WellsFargo Java Training Sprint Template
PROJECT NAME: LOAN MANAGMENT SYSTEM - JAVA WITH REACT CASE STUDY |  |  |  | Trainer |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
Batch #: |  | Group #: 1 , | Particiaonts name: Sai Teja Reddy Tileti Akshat Mudgal Shreya Srikrishna Ankit Jha |  |  |  | 2023-08-08 | 2023-08-29 | 4.545% | SCOPE STATEMENT
At Risk? | SPRINT # | USER STORY | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Yes | SPRINT - 01 Setup & User Authentication | US-01 - As a developer, develop a well-organized project layout and be able to create an initial React application that includes the ability to navigate between different pages. | 1. Set up a new React project using Create React App |  | SaiTeja |  | 2023-09-06 | 2023-09-06 | 1 | Complete | High
No |  |  | 2. Install and configure React Router for handling routing in the application |  | SaiTeja |  | 2023-09-06 | 2023-09-06 |  | Complete | Medium
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | Shreya, Akshat |  | 2023-09-06 | 2023-09-06 |  | Complete | Low
|  | US_02 - As a database developer, you need to easily establish the necessary database structure and create the required databases and tables to efficiently store and manage my data. | 1. Design the database schema for the online banking system |  | Ankit |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 2. Create the table for registered users |  | User 2 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 3. Create the table for the account |  | User 3 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 4. Create the table for Transactions |  | User 4 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 5. Populate all the above tables with sample data space |  | User 5 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  | US_03 - As a frontend developer, create a user registration form that allows end user to fill out details and register as a new user, and have that information securely processed by the backend system. | 1. Create a react page to read user details and provide proper validations at backend |  | User 1 |  | 2023-09-07 | 2023-09-07 | 1 | Not Started
|  |  | 2. Write a proper api end point in springboot to read data from frontend and insert into database |  | User 2 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  |  | 3. Perform all sorts of validations using springboot's validators |  | User 3 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  | US_04 - As a frontend user, develop a secure way to access the application through a login page for an end user to authenticate and ensure only authorized individuals can access the system. | 1. create a react login page to read username and password |  | User 1 |  | 2023-08-10 | 2023-08-10 | 1 | Not Started
|  |  | 2. Include the Authentication and Authorization techniques |  | User 2 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 3.Write a proper api's to read data from front end and implement authentication and authorization using spring security |  | User 3 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 4. Implement authentication using JWT |  | User 4 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 5. Perform the session management |  | User 5 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  | US_05 - As a developer, create a user-friendly form that allows end user to create a new account as a registered user and the information provided by the end user to be securely processed by the backend system and accurately stored in the database. | 1. Create a react form to create a new account for registered users |  | User 1 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 2. upon successful adding the data, it should generate a unique id, which should also sent along with other details for backend processing. |  | User 2 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 3. Write the backend springboot api's to read account details and add it to database |  | User 3 |  | 2028-08-10 | 2028-08-10 |  | Not Started
| SPRINT - 02 Account Management & User Dashboard | US_07 - As a developer, create a visually appealing dashboard for the end user that provides easy access to a range of operations and tasks they can perform. This dashboard should enable end user to conveniently navigate through different features and carry out various actions. | 1. Design the user interface for the user dashboard. |  | User 1 |  | 2028-08-11 | 2028-08-11 | 1 | Not Started
|  |  | 2. Implement the user dashboard page in React. |  | User 2 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 3. Connect the user dashboard to the backend API to fetch relevant data. write the springboot implementation to fetch all user data for respective user and send to UI |  | User 3 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 4. Implement functionality in the user dashboard, such as View Loans, Items Purchased, Apply for Loan |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 5. Test the user dashboard's functionality and user experience. |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  | US_08 - As a developer, create the a dashboard to end user to view loan cards & Apply Loan. Create a backend layer to support view loan and loan processing. | 1. Create a page for user to purchase a product from the available list, by providing the appropriate details, with acceptance criteria as mentioned |  | User 1 |  | 2028-08-14 | 2028-08-14 | 1 | Not Started
|  |  | 2. An user should be able to view all the loan cards availed with criteria It should display only the active loan cards. |  | User 2 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object. Read the loan details from UI and pass it to service layer further to do layer based on item selected, it should identify the appropriate card type and amount, do the processing . Must use POST method of communication |  | User 3 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 4. Based on the employee id logged in, it should find and display the appropriate active loans Must use POST method of communication |  | User 4 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  | US_09 - As a developer, create a front end page to perform purchase and show the purchase history. | 1. Create a react page to view all the items purchased. It should display all the products which are purchased, both active loans and completed loans. |  | User 1 |  | 2028-08-16 | 2028-08-16 | 1 | Not Started
|  |  | 2. Should be able to extract the values from request body object |  | User 2 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 3. Based on the employee id logged in, it should find all the items purchased by the employee and returns them in the form of grid. |  | User 3 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | Must use POST method of communication |  | User 4 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 5. write the backend processing to read the data from database and send it to frontend. It must have a provision to redirect to home or dashboard upon successful display. |  | User 5 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  | US_10 - As a developer, test and ensure that all the front end and backend units are working fine and integrated successfully. Make sure that the end user to have a smooth and error-free experience when using the application. | 1. Write unit tests to ensure the functionality of critical components |  | User 1 |  | 2028-08-17 | 2028-08-17 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 2 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 3 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  | US_11 - As a frontend developer, create a admin page that allows admin to provide the user id and password for validation. | 1. DB Schema creation and setup in mysql database 2. Spring boot project setup creation. 3. Develop the post method api to read data from view page. 4. Use appropriate DTO objects for view and data integration 5. Use spring data jpa for connecting to databases. |  | User 1 &2 |  | 2028-08-18 | 2028-08-18 | 1 | Not Started
|  |  | 6. Set up the appropriate methods to perform functions like user validation, user registration, transaction management, transaction details. |  | User 3 &4 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 7. Both username and password are mandatory, if not provided, error messages should be displayed. |  | User 5 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 8. Successful validation should redirect to menu page, unsuccessful validation should redirect to registration page. |  |  |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  | US_12 - As a developer, create a front end admin login page, display the Admin Dashboard for Loan, Customer and Item Master details management. Create a backend layer to support view Loan Card Details Management processing | 1. Should be able to extract the values from request body object |  |  |  | 2028-08-21 | 2028-08-21 | 1 | Not Started
|  |  | 2. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database. |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 3. Should return the model object after successful insertion of data |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 4. Must use POST method of communication |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  | US_13 - As a developer, create a front end admin page to 1. To create a new loan card with the following details viz., loand_id, loan_type, duration_in_years and should save it in the database. 2. To create a new employee with the following details: viz., employee_id, employee_name, designation, department, gender, date_of_birth, date_of_joining. | 1. Once the loan card data is entered, it should redirect to display all the existing loan card details and also have a provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 | 1 | Not Started
|  |  | 2. Once the employee data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 4. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 5. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 6. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  | US_14 - As a developer, create a front end admin page with item management, to create a new item details Create a backend layer to support on item master management | 1. As an admin he should be able to create a new item details with the following details: viz., item_id, item_description, issue_status, item_make, item_category, item_valuation. |  |  |  | 2028-08-23 | 2028-08-23 | 1 | Not Started
|  |  | 2.Once the data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object, 4. Should return the model object after successful insertion of data 5. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 6. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 7. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
Yes | SPRINT - 03 Error handling & Design Enhancement | US_11 - As a developer, implement a proper error handling mechanism, so that the end user, to receives a clear and understandable error messages to know what went wrong. | 1. Create a custom exception objects in backend to raise when user details not found, insufficient balance, no transactions etc., |  | User 1 |  | 2028-08-24 | 2028-08-24 | 1 | Not Started | High
No |  |  | Implement the custom exception logic at UI level |  | User 2 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Medium
|  |  | 2. All input validations logic must be performed at UI level |  | User 3 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Low
|  |  | 3. All data validations must be performed at backend |  | User 1 |  | 2028-08-24 | 2028-08-24 |  | Not Started
|  | US_12 - As a developer, rigourously test the app and ensure all the front end and backend units are working fine and integrated successfully | 1. Write unit tests to ensure the functionality of critical components |  | User 2 |  | 2028-08-25 | 2028-08-25 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 3 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 4 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  | US_13 - UI Design Enhancements - Make sure there is an improvements in the overall design and user interface of the application to enhance the user experience and make it more visually appealing. | 1. Design the Front-End UI of the application with proper Home Page |  | User 1 |  | 2028-08-28 | 2028-08-28 | 1 | Not Started
|  |  | 2. Improve the user interface by adding responsive design, styling, and enhancing the user experience |  | User 2 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  |  | 3. Ensure accessibility and compatibility across different browsers |  | User 3 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  | Final Project Presentation |  |  |  |  | 2028-08-29 | 2028-08-29 | 1 | Not Started

## Batch6-Group4
WellsFargo Java Training Sprint Template
PROJECT NAME: LOAN MANAGMENT SYSTEM - JAVA WITH REACT CASE STUDY |  |  |  | Trainer |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
Batch #: |  | Group #: 1 , | Particiaonts name: Venkata Subhash Raja Srikrishnan Ravichandran Atishay Patni Oishwarjya Banerjee |  |  |  | 2023-09-06 | 2023-08-29 | 4.545% | SCOPE STATEMENT
At Risk? | SPRINT # | USER STORY | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Yes | SPRINT - 01 Setup & User Authentication | US-01 - As a developer, develop a well-organized project layout and be able to create an initial React application that includes the ability to navigate between different pages. | 1. Set up a new React project using Create React App |  | Atishay, Shrikrishna |  | 2023-09-06 | 2023-09-06 | 1 | Complete | High
No |  |  | 2. Install and configure React Router for handling routing in the application |  | Atishay, Shrikirshna |  | 2023-09-06 | 2023-09-06 |  | Complete | Medium
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | Oishwarya,Subhash |  | 2023-09-06 | 2023-09-06 |  | Complete | Low
|  | US_02 - As a database developer, you need to easily establish the necessary database structure and create the required databases and tables to efficiently store and manage my data. | 1. Design the database schema for the online banking system |  | User 1 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 2. Create the table for registered users |  | User 2 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 3. Create the table for the account |  | User 3 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 4. Create the table for Transactions |  | User 4 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 5. Populate all the above tables with sample data space |  | User 5 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  | US_03 - As a frontend developer, create a user registration form that allows end user to fill out details and register as a new user, and have that information securely processed by the backend system. | 1. Create a react page to read user details and provide proper validations at backend |  | User 1 |  | 2023-09-07 | 2023-09-07 | 1 | Not Started
|  |  | 2. Write a proper api end point in springboot to read data from frontend and insert into database |  | User 2 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  |  | 3. Perform all sorts of validations using springboot's validators |  | User 3 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  | US_04 - As a frontend user, develop a secure way to access the application through a login page for an end user to authenticate and ensure only authorized individuals can access the system. | 1. create a react login page to read username and password |  | User 1 |  | 2023-08-10 | 2023-08-10 | 1 | Not Started
|  |  | 2. Include the Authentication and Authorization techniques |  | User 2 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 3.Write a proper api's to read data from front end and implement authentication and authorization using spring security |  | User 3 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 4. Implement authentication using JWT |  | User 4 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 5. Perform the session management |  | User 5 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  | US_05 - As a developer, create a user-friendly form that allows end user to create a new account as a registered user and the information provided by the end user to be securely processed by the backend system and accurately stored in the database. | 1. Create a react form to create a new account for registered users |  | User 1 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 2. upon successful adding the data, it should generate a unique id, which should also sent along with other details for backend processing. |  | User 2 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 3. Write the backend springboot api's to read account details and add it to database |  | User 3 |  | 2028-08-10 | 2028-08-10 |  | Not Started
| SPRINT - 02 Account Management & User Dashboard | US_07 - As a developer, create a visually appealing dashboard for the end user that provides easy access to a range of operations and tasks they can perform. This dashboard should enable end user to conveniently navigate through different features and carry out various actions. | 1. Design the user interface for the user dashboard. |  | User 1 |  | 2028-08-11 | 2028-08-11 | 1 | Not Started
|  |  | 2. Implement the user dashboard page in React. |  | User 2 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 3. Connect the user dashboard to the backend API to fetch relevant data. write the springboot implementation to fetch all user data for respective user and send to UI |  | User 3 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 4. Implement functionality in the user dashboard, such as View Loans, Items Purchased, Apply for Loan |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 5. Test the user dashboard's functionality and user experience. |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  | US_08 - As a developer, create the a dashboard to end user to view loan cards & Apply Loan. Create a backend layer to support view loan and loan processing. | 1. Create a page for user to purchase a product from the available list, by providing the appropriate details, with acceptance criteria as mentioned |  | User 1 |  | 2028-08-14 | 2028-08-14 | 1 | Not Started
|  |  | 2. An user should be able to view all the loan cards availed with criteria It should display only the active loan cards. |  | User 2 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object. Read the loan details from UI and pass it to service layer further to do layer based on item selected, it should identify the appropriate card type and amount, do the processing . Must use POST method of communication |  | User 3 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 4. Based on the employee id logged in, it should find and display the appropriate active loans Must use POST method of communication |  | User 4 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  | US_09 - As a developer, create a front end page to perform purchase and show the purchase history. | 1. Create a react page to view all the items purchased. It should display all the products which are purchased, both active loans and completed loans. |  | User 1 |  | 2028-08-16 | 2028-08-16 | 1 | Not Started
|  |  | 2. Should be able to extract the values from request body object |  | User 2 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 3. Based on the employee id logged in, it should find all the items purchased by the employee and returns them in the form of grid. |  | User 3 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | Must use POST method of communication |  | User 4 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 5. write the backend processing to read the data from database and send it to frontend. It must have a provision to redirect to home or dashboard upon successful display. |  | User 5 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  | US_10 - As a developer, test and ensure that all the front end and backend units are working fine and integrated successfully. Make sure that the end user to have a smooth and error-free experience when using the application. | 1. Write unit tests to ensure the functionality of critical components |  | User 1 |  | 2028-08-17 | 2028-08-17 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 2 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 3 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  | US_11 - As a frontend developer, create a admin page that allows admin to provide the user id and password for validation. | 1. DB Schema creation and setup in mysql database 2. Spring boot project setup creation. 3. Develop the post method api to read data from view page. 4. Use appropriate DTO objects for view and data integration 5. Use spring data jpa for connecting to databases. |  | User 1 &2 |  | 2028-08-18 | 2028-08-18 | 1 | Not Started
|  |  | 6. Set up the appropriate methods to perform functions like user validation, user registration, transaction management, transaction details. |  | User 3 &4 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 7. Both username and password are mandatory, if not provided, error messages should be displayed. |  | User 5 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 8. Successful validation should redirect to menu page, unsuccessful validation should redirect to registration page. |  |  |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  | US_12 - As a developer, create a front end admin login page, display the Admin Dashboard for Loan, Customer and Item Master details management. Create a backend layer to support view Loan Card Details Management processing | 1. Should be able to extract the values from request body object |  |  |  | 2028-08-21 | 2028-08-21 | 1 | Not Started
|  |  | 2. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database. |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 3. Should return the model object after successful insertion of data |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 4. Must use POST method of communication |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  | US_13 - As a developer, create a front end admin page to 1. To create a new loan card with the following details viz., loand_id, loan_type, duration_in_years and should save it in the database. 2. To create a new employee with the following details: viz., employee_id, employee_name, designation, department, gender, date_of_birth, date_of_joining. | 1. Once the loan card data is entered, it should redirect to display all the existing loan card details and also have a provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 | 1 | Not Started
|  |  | 2. Once the employee data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 4. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 5. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 6. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  | US_14 - As a developer, create a front end admin page with item management, to create a new item details Create a backend layer to support on item master management | 1. As an admin he should be able to create a new item details with the following details: viz., item_id, item_description, issue_status, item_make, item_category, item_valuation. |  |  |  | 2028-08-23 | 2028-08-23 | 1 | Not Started
|  |  | 2.Once the data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object, 4. Should return the model object after successful insertion of data 5. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 6. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 7. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
Yes | SPRINT - 03 Error handling & Design Enhancement | US_11 - As a developer, implement a proper error handling mechanism, so that the end user, to receives a clear and understandable error messages to know what went wrong. | 1. Create a custom exception objects in backend to raise when user details not found, insufficient balance, no transactions etc., |  | User 1 |  | 2028-08-24 | 2028-08-24 | 1 | Not Started | High
No |  |  | Implement the custom exception logic at UI level |  | User 2 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Medium
|  |  | 2. All input validations logic must be performed at UI level |  | User 3 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Low
|  |  | 3. All data validations must be performed at backend |  | User 1 |  | 2028-08-24 | 2028-08-24 |  | Not Started
|  | US_12 - As a developer, rigourously test the app and ensure all the front end and backend units are working fine and integrated successfully | 1. Write unit tests to ensure the functionality of critical components |  | User 2 |  | 2028-08-25 | 2028-08-25 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 3 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 4 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  | US_13 - UI Design Enhancements - Make sure there is an improvements in the overall design and user interface of the application to enhance the user experience and make it more visually appealing. | 1. Design the Front-End UI of the application with proper Home Page |  | User 1 |  | 2028-08-28 | 2028-08-28 | 1 | Not Started
|  |  | 2. Improve the user interface by adding responsive design, styling, and enhancing the user experience |  | User 2 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  |  | 3. Ensure accessibility and compatibility across different browsers |  | User 3 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  | Final Project Presentation |  |  |  |  | 2028-08-29 | 2028-08-29 | 1 | Not Started

## Batch6-Group5
WellsFargo Java Training Sprint Template
PROJECT NAME: LOAN MANAGMENT SYSTEM - JAVA WITH REACT CASE STUDY |  |  |  | Trainer |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
Batch #: |  | Group #: 1 , | Particiaonts name:Avad Agarwal Snehasish Roy Sankeerth Sankar Saurabh Patra |  |  |  | 2023-09-06 | 2023-08-29 | 9.091% | SCOPE STATEMENT
At Risk? | SPRINT # | USER STORY | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Yes | SPRINT - 01 Setup & User Authentication | US-01 - As a developer, develop a well-organized project layout and be able to create an initial React application that includes the ability to navigate between different pages. | 1. Set up a new React project using Create React App |  | Snehashish |  | 2023-09-06 | 2023-09-06 | 1 | Complete | High
No |  |  | 2. Install and configure React Router for handling routing in the application |  | Snehashish |  | 2023-09-06 | 2023-09-06 |  | In Progress | Medium
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | Saurabh |  | 2023-09-06 | 2023-09-06 |  | Complete | Low
|  | US_02 - As a database developer, you need to easily establish the necessary database structure and create the required databases and tables to efficiently store and manage my data. | 1. Design the database schema for the online banking system |  | Sankeerth |  | 2023-09-06 | 2023-09-06 |  | Complete
|  |  | 2. Create the table for registered users |  | Sankeerth |  | 2023-09-06 | 2023-09-06 |  | Complete
|  |  | 3. Create the table for the account |  | Avad |  | 2023-09-06 | 2023-09-06 |  | Complete
|  |  | 4. Create the table for Transactions |  | Avad |  | 2023-09-06 | 2023-09-06 |  | Complete
|  |  | 5. Populate all the above tables with sample data space |  | User 5 |  | 2023-09-06 | 2023-09-06 |  | In Progress
|  | US_03 - As a frontend developer, create a user registration form that allows end user to fill out details and register as a new user, and have that information securely processed by the backend system. | 1. Create a react page to read user details and provide proper validations at backend |  | User 1 |  | 2023-09-07 | 2023-09-07 | 1 | Not Started
|  |  | 2. Write a proper api end point in springboot to read data from frontend and insert into database |  | User 2 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  |  | 3. Perform all sorts of validations using springboot's validators |  | User 3 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  | US_04 - As a frontend user, develop a secure way to access the application through a login page for an end user to authenticate and ensure only authorized individuals can access the system. | 1. create a react login page to read username and password |  | User 1 |  | 2023-08-10 | 2023-08-10 | 1 | Not Started
|  |  | 2. Include the Authentication and Authorization techniques |  | User 2 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 3.Write a proper api's to read data from front end and implement authentication and authorization using spring security |  | User 3 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 4. Implement authentication using JWT |  | User 4 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 5. Perform the session management |  | User 5 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  | US_05 - As a developer, create a user-friendly form that allows end user to create a new account as a registered user and the information provided by the end user to be securely processed by the backend system and accurately stored in the database. | 1. Create a react form to create a new account for registered users |  | User 1 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 2. upon successful adding the data, it should generate a unique id, which should also sent along with other details for backend processing. |  | User 2 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 3. Write the backend springboot api's to read account details and add it to database |  | User 3 |  | 2028-08-10 | 2028-08-10 |  | Not Started
| SPRINT - 02 Account Management & User Dashboard | US_07 - As a developer, create a visually appealing dashboard for the end user that provides easy access to a range of operations and tasks they can perform. This dashboard should enable end user to conveniently navigate through different features and carry out various actions. | 1. Design the user interface for the user dashboard. |  | User 1 |  | 2028-08-11 | 2028-08-11 | 1 | Not Started
|  |  | 2. Implement the user dashboard page in React. |  | User 2 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 3. Connect the user dashboard to the backend API to fetch relevant data. write the springboot implementation to fetch all user data for respective user and send to UI |  | User 3 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 4. Implement functionality in the user dashboard, such as View Loans, Items Purchased, Apply for Loan |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 5. Test the user dashboard's functionality and user experience. |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  | US_08 - As a developer, create the a dashboard to end user to view loan cards & Apply Loan. Create a backend layer to support view loan and loan processing. | 1. Create a page for user to purchase a product from the available list, by providing the appropriate details, with acceptance criteria as mentioned |  | User 1 |  | 2028-08-14 | 2028-08-14 | 1 | Not Started
|  |  | 2. An user should be able to view all the loan cards availed with criteria It should display only the active loan cards. |  | User 2 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object. Read the loan details from UI and pass it to service layer further to do layer based on item selected, it should identify the appropriate card type and amount, do the processing . Must use POST method of communication |  | User 3 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 4. Based on the employee id logged in, it should find and display the appropriate active loans Must use POST method of communication |  | User 4 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  | US_09 - As a developer, create a front end page to perform purchase and show the purchase history. | 1. Create a react page to view all the items purchased. It should display all the products which are purchased, both active loans and completed loans. |  | User 1 |  | 2028-08-16 | 2028-08-16 | 1 | Not Started
|  |  | 2. Should be able to extract the values from request body object |  | User 2 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 3. Based on the employee id logged in, it should find all the items purchased by the employee and returns them in the form of grid. |  | User 3 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | Must use POST method of communication |  | User 4 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 5. write the backend processing to read the data from database and send it to frontend. It must have a provision to redirect to home or dashboard upon successful display. |  | User 5 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  | US_10 - As a developer, test and ensure that all the front end and backend units are working fine and integrated successfully. Make sure that the end user to have a smooth and error-free experience when using the application. | 1. Write unit tests to ensure the functionality of critical components |  | User 1 |  | 2028-08-17 | 2028-08-17 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 2 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 3 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  | US_11 - As a frontend developer, create a admin page that allows admin to provide the user id and password for validation. | 1. DB Schema creation and setup in mysql database 2. Spring boot project setup creation. 3. Develop the post method api to read data from view page. 4. Use appropriate DTO objects for view and data integration 5. Use spring data jpa for connecting to databases. |  | User 1 &2 |  | 2028-08-18 | 2028-08-18 | 1 | Not Started
|  |  | 6. Set up the appropriate methods to perform functions like user validation, user registration, transaction management, transaction details. |  | User 3 &4 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 7. Both username and password are mandatory, if not provided, error messages should be displayed. |  | User 5 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 8. Successful validation should redirect to menu page, unsuccessful validation should redirect to registration page. |  |  |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  | US_12 - As a developer, create a front end admin login page, display the Admin Dashboard for Loan, Customer and Item Master details management. Create a backend layer to support view Loan Card Details Management processing | 1. Should be able to extract the values from request body object |  |  |  | 2028-08-21 | 2028-08-21 | 1 | Not Started
|  |  | 2. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database. |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 3. Should return the model object after successful insertion of data |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 4. Must use POST method of communication |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  | US_13 - As a developer, create a front end admin page to 1. To create a new loan card with the following details viz., loand_id, loan_type, duration_in_years and should save it in the database. 2. To create a new employee with the following details: viz., employee_id, employee_name, designation, department, gender, date_of_birth, date_of_joining. | 1. Once the loan card data is entered, it should redirect to display all the existing loan card details and also have a provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 | 1 | Not Started
|  |  | 2. Once the employee data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 4. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 5. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 6. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  | US_14 - As a developer, create a front end admin page with item management, to create a new item details Create a backend layer to support on item master management | 1. As an admin he should be able to create a new item details with the following details: viz., item_id, item_description, issue_status, item_make, item_category, item_valuation. |  |  |  | 2028-08-23 | 2028-08-23 | 1 | Not Started
|  |  | 2.Once the data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object, 4. Should return the model object after successful insertion of data 5. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 6. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 7. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
Yes | SPRINT - 03 Error handling & Design Enhancement | US_11 - As a developer, implement a proper error handling mechanism, so that the end user, to receives a clear and understandable error messages to know what went wrong. | 1. Create a custom exception objects in backend to raise when user details not found, insufficient balance, no transactions etc., |  | User 1 |  | 2028-08-24 | 2028-08-24 | 1 | Not Started | High
No |  |  | Implement the custom exception logic at UI level |  | User 2 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Medium
|  |  | 2. All input validations logic must be performed at UI level |  | User 3 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Low
|  |  | 3. All data validations must be performed at backend |  | User 1 |  | 2028-08-24 | 2028-08-24 |  | Not Started
|  | US_12 - As a developer, rigourously test the app and ensure all the front end and backend units are working fine and integrated successfully | 1. Write unit tests to ensure the functionality of critical components |  | User 2 |  | 2028-08-25 | 2028-08-25 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 3 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 4 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  | US_13 - UI Design Enhancements - Make sure there is an improvements in the overall design and user interface of the application to enhance the user experience and make it more visually appealing. | 1. Design the Front-End UI of the application with proper Home Page |  | User 1 |  | 2028-08-28 | 2028-08-28 | 1 | Not Started
|  |  | 2. Improve the user interface by adding responsive design, styling, and enhancing the user experience |  | User 2 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  |  | 3. Ensure accessibility and compatibility across different browsers |  | User 3 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  | Final Project Presentation |  |  |  |  | 2028-08-29 | 2028-08-29 | 1 | Not Started

## Batch6-Group6
WellsFargo Java Training Sprint Template
PROJECT NAME: LOAN MANAGMENT SYSTEM - JAVA WITH REACT CASE STUDY |  |  |  | Trainer |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
Batch #: |  | Group #: 1 , | Particiaonts name:Saurav Kumar Shashank Hara Sridhar Pranav Sharma Ankit Sibi Cherian |  |  |  | 2023-09-06 | 2023-08-29 | 4.545% | SCOPE STATEMENT
At Risk? | SPRINT # | USER STORY | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Yes | SPRINT - 01 Setup & User Authentication | US-01 - As a developer, develop a well-organized project layout and be able to create an initial React application that includes the ability to navigate between different pages. | 1. Set up a new React project using Create React App |  | Saurav, Shashank |  | 2023-09-06 | 2023-09-06 | 1 | Complete | High
No |  |  | 2. Install and configure React Router for handling routing in the application |  | Saurav, Shashank |  | 2023-09-06 | 2023-09-06 |  | Complete | Medium
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | Pranav, Ankit |  | 2023-09-06 | 2023-09-06 |  | Complete | Low
|  | US_02 - As a database developer, you need to easily establish the necessary database structure and create the required databases and tables to efficiently store and manage my data. | 1. Design the database schema for the online banking system |  | User 1 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 2. Create the table for registered users |  | User 2 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 3. Create the table for the account |  | User 3 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 4. Create the table for Transactions |  | User 4 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  |  | 5. Populate all the above tables with sample data space |  | User 5 |  | 2023-09-06 | 2023-09-06 |  | Not Started
|  | US_03 - As a frontend developer, create a user registration form that allows end user to fill out details and register as a new user, and have that information securely processed by the backend system. | 1. Create a react page to read user details and provide proper validations at backend |  | User 1 |  | 2023-09-07 | 2023-09-07 | 1 | Not Started
|  |  | 2. Write a proper api end point in springboot to read data from frontend and insert into database |  | User 2 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  |  | 3. Perform all sorts of validations using springboot's validators |  | User 3 |  | 2023-09-07 | 2023-09-07 |  | Not Started
|  | US_04 - As a frontend user, develop a secure way to access the application through a login page for an end user to authenticate and ensure only authorized individuals can access the system. | 1. create a react login page to read username and password |  | User 1 |  | 2023-08-10 | 2023-08-10 | 1 | Not Started
|  |  | 2. Include the Authentication and Authorization techniques |  | User 2 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 3.Write a proper api's to read data from front end and implement authentication and authorization using spring security |  | User 3 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 4. Implement authentication using JWT |  | User 4 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  |  | 5. Perform the session management |  | User 5 |  | 2023-08-10 | 2023-08-10 |  | Not Started
|  | US_05 - As a developer, create a user-friendly form that allows end user to create a new account as a registered user and the information provided by the end user to be securely processed by the backend system and accurately stored in the database. | 1. Create a react form to create a new account for registered users |  | User 1 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 2. upon successful adding the data, it should generate a unique id, which should also sent along with other details for backend processing. |  | User 2 |  | 2028-08-10 | 2028-08-10 |  | Not Started
|  |  | 3. Write the backend springboot api's to read account details and add it to database |  | User 3 |  | 2028-08-10 | 2028-08-10 |  | Not Started
| SPRINT - 02 Account Management & User Dashboard | US_07 - As a developer, create a visually appealing dashboard for the end user that provides easy access to a range of operations and tasks they can perform. This dashboard should enable end user to conveniently navigate through different features and carry out various actions. | 1. Design the user interface for the user dashboard. |  | User 1 |  | 2028-08-11 | 2028-08-11 | 1 | Not Started
|  |  | 2. Implement the user dashboard page in React. |  | User 2 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 3. Connect the user dashboard to the backend API to fetch relevant data. write the springboot implementation to fetch all user data for respective user and send to UI |  | User 3 |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 4. Implement functionality in the user dashboard, such as View Loans, Items Purchased, Apply for Loan |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  |  | 5. Test the user dashboard's functionality and user experience. |  |  |  | 2028-08-11 | 2028-08-11 |  | Not Started
|  | US_08 - As a developer, create the a dashboard to end user to view loan cards & Apply Loan. Create a backend layer to support view loan and loan processing. | 1. Create a page for user to purchase a product from the available list, by providing the appropriate details, with acceptance criteria as mentioned |  | User 1 |  | 2028-08-14 | 2028-08-14 | 1 | Not Started
|  |  | 2. An user should be able to view all the loan cards availed with criteria It should display only the active loan cards. |  | User 2 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object. Read the loan details from UI and pass it to service layer further to do layer based on item selected, it should identify the appropriate card type and amount, do the processing . Must use POST method of communication |  | User 3 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  |  | 4. Based on the employee id logged in, it should find and display the appropriate active loans Must use POST method of communication |  | User 4 |  | 2028-08-14 | 2028-08-14 |  | Not Started
|  | US_09 - As a developer, create a front end page to perform purchase and show the purchase history. | 1. Create a react page to view all the items purchased. It should display all the products which are purchased, both active loans and completed loans. |  | User 1 |  | 2028-08-16 | 2028-08-16 | 1 | Not Started
|  |  | 2. Should be able to extract the values from request body object |  | User 2 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 3. Based on the employee id logged in, it should find all the items purchased by the employee and returns them in the form of grid. |  | User 3 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | Must use POST method of communication |  | User 4 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  |  | 5. write the backend processing to read the data from database and send it to frontend. It must have a provision to redirect to home or dashboard upon successful display. |  | User 5 |  | 2028-08-16 | 2028-08-16 |  | Not Started
|  | US_10 - As a developer, test and ensure that all the front end and backend units are working fine and integrated successfully. Make sure that the end user to have a smooth and error-free experience when using the application. | 1. Write unit tests to ensure the functionality of critical components |  | User 1 |  | 2028-08-17 | 2028-08-17 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 2 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 3 |  | 2028-08-17 | 2028-08-17 |  | Not Started
|  | US_11 - As a frontend developer, create a admin page that allows admin to provide the user id and password for validation. | 1. DB Schema creation and setup in mysql database 2. Spring boot project setup creation. 3. Develop the post method api to read data from view page. 4. Use appropriate DTO objects for view and data integration 5. Use spring data jpa for connecting to databases. |  | User 1 &2 |  | 2028-08-18 | 2028-08-18 | 1 | Not Started
|  |  | 6. Set up the appropriate methods to perform functions like user validation, user registration, transaction management, transaction details. |  | User 3 &4 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 7. Both username and password are mandatory, if not provided, error messages should be displayed. |  | User 5 |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  |  | 8. Successful validation should redirect to menu page, unsuccessful validation should redirect to registration page. |  |  |  | 2028-08-18 | 2028-08-18 |  | Not Started
|  | US_12 - As a developer, create a front end admin login page, display the Admin Dashboard for Loan, Customer and Item Master details management. Create a backend layer to support view Loan Card Details Management processing | 1. Should be able to extract the values from request body object |  |  |  | 2028-08-21 | 2028-08-21 | 1 | Not Started
|  |  | 2. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database. |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 3. Should return the model object after successful insertion of data |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  |  | 4. Must use POST method of communication |  |  |  | 2028-08-21 | 2028-08-21 |  | Not Started
|  | US_13 - As a developer, create a front end admin page to 1. To create a new loan card with the following details viz., loand_id, loan_type, duration_in_years and should save it in the database. 2. To create a new employee with the following details: viz., employee_id, employee_name, designation, department, gender, date_of_birth, date_of_joining. | 1. Once the loan card data is entered, it should redirect to display all the existing loan card details and also have a provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 | 1 | Not Started
|  |  | 2. Once the employee data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 4. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 5. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  |  | 6. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-22 | 2028-08-22 |  | Not Started
|  | US_14 - As a developer, create a front end admin page with item management, to create a new item details Create a backend layer to support on item master management | 1. As an admin he should be able to create a new item details with the following details: viz., item_id, item_description, issue_status, item_make, item_category, item_valuation. |  |  |  | 2028-08-23 | 2028-08-23 | 1 | Not Started
|  |  | 2.Once the data is entered and submitted, it should save the details in the database and also have the provision to edit and delete existing data details. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 3. Should be able to extract the values from request body object, 4. Should return the model object after successful insertion of data 5. Read the user registration values from UI and pass it to service layer further to dao layer to perform insertion of record in database |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 6. Once data is inserted, it should re direct to display all the details of loans |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
|  |  | 7. If insertion fails, it should display an error page and must have provision to go to menu page. |  |  |  | 2028-08-23 | 2028-08-23 |  | Not Started
Yes | SPRINT - 03 Error handling & Design Enhancement | US_11 - As a developer, implement a proper error handling mechanism, so that the end user, to receives a clear and understandable error messages to know what went wrong. | 1. Create a custom exception objects in backend to raise when user details not found, insufficient balance, no transactions etc., |  | User 1 |  | 2028-08-24 | 2028-08-24 | 1 | Not Started | High
No |  |  | Implement the custom exception logic at UI level |  | User 2 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Medium
|  |  | 2. All input validations logic must be performed at UI level |  | User 3 |  | 2028-08-24 | 2028-08-24 |  | Not Started | Low
|  |  | 3. All data validations must be performed at backend |  | User 1 |  | 2028-08-24 | 2028-08-24 |  | Not Started
|  | US_12 - As a developer, rigourously test the app and ensure all the front end and backend units are working fine and integrated successfully | 1. Write unit tests to ensure the functionality of critical components |  | User 2 |  | 2028-08-25 | 2028-08-25 | 1 | Not Started
|  |  | 2. Perform integration testing to validate the interaction between frontend and backend |  | User 3 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  |  | 3. Set up a new springboot project and all the required dependencies and test working fine or not |  | User 4 |  | 2028-08-25 | 2028-08-25 |  | Not Started
|  | US_13 - UI Design Enhancements - Make sure there is an improvements in the overall design and user interface of the application to enhance the user experience and make it more visually appealing. | 1. Design the Front-End UI of the application with proper Home Page |  | User 1 |  | 2028-08-28 | 2028-08-28 | 1 | Not Started
|  |  | 2. Improve the user interface by adding responsive design, styling, and enhancing the user experience |  | User 2 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  |  | 3. Ensure accessibility and compatibility across different browsers |  | User 3 |  | 2028-08-28 | 2028-08-28 |  | Not Started
|  | Final Project Presentation |  |  |  |  | 2028-08-29 | 2028-08-29 | 1 | Not Started

## Meeting Agenda
Meeting Ethic:
Respect: Treat all team members with respect and value their contributions and ideas.
Active Listening: Listen attentively to each team member during discussions and avoid interrupting.
Collaboration: Encourage open communication and collaboration among team members.
Time Management: Adhere to the meeting agenda and ensure that discussions stay focused and on track.
Accountability: Take ownership of assigned tasks and update the team on progress and challenges.
Constructive Feedback: Provide feedback in a constructive and supportive manner to help improve team performance.
Confidentiality: Maintain the confidentiality of sensitive project information and user data discussed during the meeting.
Professionalism: Maintain a professional and positive attitude throughout the meeting.
Equality: Ensure that all team members have equal opportunity to share their thoughts and opinions.
Problem Solving: Work together to identify and address challenges and find effective solutions.
Agenda:
1. Sprint Review | 2. Sprint Planning
Recap the progress and achievements of the previous sprint. | Review the user stories and tasks for the current sprint.
Discuss any completed user stories or tasks from the previous sprint. | Clarify any doubts or questions regarding the requirements or tasks.
Address any challenges or issues encountered during the previous sprint. | Assign tasks to team members based on their skills and availability.
Estimate the effort required for each task and determine the sprint goal.
3. Daily Stand-up | 4. Sprint Progress
Each team member answers the following three questions: | Track the progress of each user story and task within the current sprint.
What tasks did you complete yesterday? | Update the task board or project management tool with the status of each task.
What tasks will you work on today? | Discuss any issues or delays that may affect the sprint timeline.
Are there any challenges or blockers impeding your progress? | Adjust task priorities or reallocate resources if necessary.
Discuss any dependencies or coordination required between team members.
Encourage collaboration and offer assistance if any team member is facing difficulties.
5. Sprint Retrospective | 6. Sprint Goals and Next Steps
Reflect on the overall sprint performance and team dynamics. | Recap the sprint goals and reiterate the importance of meeting them.
Identify what went well and should be continued in future sprints. | Define specific tasks and targets for the upcoming days.
Discuss any areas for improvement or challenges faced during the sprint. | Confirm any additional requirements, changes, or adjustments to the project plan.
Brainstorm and propose solutions or strategies to address the identified issues. | Communicate any important announcements or updates related to the project.
7. Closing Remarks
Summarize the key points discussed during the meeting.
Emphasize the importance of collaboration, communication, and teamwork.
Confirm the date, time, and agenda for the next scrum meeting.
Encourage team members to reach out for any further clarification or support.
Note: It is essential to adhere to the ethical guidelines and maintain a positive and inclusive environment throughout the scrum meeting. Respectful communication, active participation, and adherence to the agenda will contribute to the successful completion of the online banking system project.

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold